NATIONAL PENSIONS REVIEW

PROGRESS REPORT

BY

THE PENSIONS BOARD

TO

SÉAMUS BRENNAN T.D.

MINISTER FOR SOCIAL AND FAMILY AFFAIRS

29 JUNE 2005

NATIONAL PENSIONS REVIEW

PROGRESS REPORT

Section										Page

- Background								3

- Scope and Main Components of Review					4 - 5

- Process and Project Plan							6 - 7

- Various Work Projects							8

- External Consultancy Projects						9 - 11

- Consultation								12

- Pensions Board Workshops						13

- Pension Systems for Assessment					14 - 16

- Timeframe									17

- Final Report – Contents							18 - 19

- BACKGROUND

The Pensions Act requires the Minister for Social and Family Affairs to cause a report in relation to the extent of the application of occupational and other pensions, and in respect of such matters as the Minister considers relevant, to be prepared and furnished to him not later than September 2006.  A copy of that report is to be laid before each House of the Oireachtas within six months after its preparation.  This effectively requires a progress review of the changes introduced in the pensions system between 2000 and 2003 in response to the National Pensions Policy Initiative.

Seamus Brennan T.D., Minister for Social and Family Affairs, wrote to the Pensions Board in February 2005 stating that the Minister saw little point in delaying the review until 2006 and, having discussed at Government, he asked the Board to undertake the full review of coverage and associated issues without delay.  The Board welcomed the opportunity for involvement in this important review and confirmed that it would proceed with the work as quickly as possible with a view to making a progress report to the Minister in June and submitting the full report by September/early October 2005.

The Board considers that the essential scope of the review is very extensive and it is the Board’s wish to prepare a report which is of high quality and supported by adequate statistics and factual information.  The Board approached the review with an open mind and, whilst increases in pension coverage were proceeding slowly, it did not have a firm view on whether or not the present system was working sufficiently well to achieve the longer term objectives of adequate retirement provision.  The Board had some concerns about the timeframe in that the length of experience of the current system was very short for the purposes of assessing whether or not it would be successful in achieving its long term objectives.  Finally, the Board did not see this review as a new National Pensions Policy Initiative but rather as a review of the system put in place on foot of the Initiative with a view to recommending possible minor or major changes.

The issue of occupational pension scheme trusteeship is one which the Board is also committed to examining in 2005 and has been so requested by the Minister.  However, this is not included in this review other than where governance is relevant to the issues being examined or discussed.

2.	SCOPE AND MAIN COMPONENTS OF REVIEW

- Review of National Pension Policy Initiative (NPPI)

To include:

- Review of NPPI’s main strategic recommendations in relation to First and Second Pillar as an integrated national pensions system.

- Review of recommended adequacy level of gross retirement income from all sources (of 50% of gross pre-retirement income).

- Review of recommended level of Social Welfare pension (of 34% of average industrial earnings with certain indexation expectations).

- Taking a view on the sustainability of the combined costs of the First Pillar target level and Exchequer commitments on public service pensions.

- An examination of the relative merits of State support via continued net tax expenditure to the Second Pillar vis-à-vis cash expenditure of equivalent amounts under an enhanced First Pillar.

- Review of coverage targets in NPPI Report (1998)

To include:

- Continued appropriateness (or otherwise) of targets (e.g. 70% of workforce aged 30 to 65 in 10+ years) in the context of changes in the social and pensions environment.

- Refinement of targets to derive a benchmark for the 2 years (to date) of the PRSA regime.

- Review of movement to date towards appropriate targets.

3. Review of current position under Second Pillar

To include:

- Current provision, structures, coverage, costs and adequacy including trends to date.

- Assessment of future outlook in the areas of coverage, costs and adequacy.

- Specific areas such as longevity, female coverage, retirement options (e.g. ARFs)/post-retirement provision, governance (insofar as it affects coverage and adequacy).

4. Options to address coverage and adequacy

To include consideration of:

- Possible further options to improve coverage within the present voluntary system (to encompass possible incentives for employers, employees and/or individuals including the INDECON Report’s proposed recommendations).

- Both the three NPPI-identified mandatory options and other possible mandatory approaches (e.g. based on the PRSI system) to increasing coverage.

- Measures to improve adequacy (including required levels of mandatory contributions, possible State interventions such as annuity provision and underpinning of Second Pillar as in J. Kehoe proposals as well as possible increases in retirement age).

This consideration would include:

- Review of systems in selected other countries in the context of examination of the options.

- Assessment of costs and economic impact of those options (taking account of sustainability of First Pillar and public service pensions at 1. above).

3.	PROCESS AND PROJECT PLAN FOR THE REVIEW

This summarises the approach being taken to the review.  It sets out the broad components of the project, how they are interrelated, and the process being adopted.

1.	Scope

The scope of the review was agreed by the Pensions Board with the Minister of Social and Family Affairs, and a copy of it is attached.  Based on this agreed scope, the review has been divided into the following projects:

	Review of NPPI targets and progress

	Review of current pension provision

	Identification and analysis of voluntary and mandatory alternatives

	Related issues

2.	Project plan

The following diagram sets out how the four projects interrelate:

| Review NPPI targets and coverage |  |  |  | Consideration of related issues |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| Current system review |  | Alternative system review |  |  |
|  |  |  |  |  |
| Costing and analysis |  | Costing and analysis |  |  |
|  |  |  |  |  |
| Final consideration |  |  |  |  |

3.	Project management

The Board has set up a Steering Committee to oversee the review.  The review is being coordinated by the Board’s Executive, who are also carrying out much of the work involved.  However, considerable additional resources are being used in order to complete the work of the review, as follows:

- Department of Social and Family Affairs

- Department of Finance

- External Consultancies.

  - Steering Committee

The Board Steering Committee is chaired by Board Member, Tom Finlay.  It includes representatives of the Social Partners, relevant Governments departments and some members with specific expertise.  The Steering Committee is scheduled to hold a minimum of six meetings.

The role of the Steering Committee is to monitor, advise, make decisions to facilitate progress of the Review, and make key decisions for recommendation to the full Board.  In this context it should be noted that final agreement on all key decisions will be ultimately a matter for the full Board.

  - Board Workshops

There are a series of Board Workshops to consider various issues, attended by Board members and others.  Details of these Workshops are described in section 7.

- VARIOUS WORK PROJECTS

The major work projects (other than external consultancy projects) identified were:

Department of Social and Family Affairs

The Department has done much of the work needed for the review of the NPPI targets, in particular in relation to the measurement of poverty.  The Department is also preparing updated estimates of the projected cost of the existing First Pillar pension provision which is being used in the review of the current pension provision system.

The projection of First Pillar costs is being prepared by the Department in close consultation with the external consultants to ensure consistency among all projections.  The results of the Department’s work will be available shortly.

Department of Finance

The Department is preparing an updated estimate of the projected cost of public service pensions, which is being included in the review of current pension system, as well as a projection of the National Pensions Reserve Fund.  Initial results are available and the project will be completed shortly.

Central Statistics Office (CSO)

The CSO Quarterly National Household Survey (QNHS) carried out in Quarter 1 2005 included a further limited survey of pension coverage.  The results of this are being processed at present and are expected to be available at end August.

Pensions Board Executive

As well as support for the Board’s NPR Steering Committee and Workshops, the Executive’s input will include drafting the text of the final report based on discussion at Steering Committee/Workshop levels, input of consultancy studies, and reflecting agreement of ultimate proposals by the Board.

5.	EXTERNAL CONSULTANCY PROJECTS

The Pensions Board commissioned four specific external consultancy projects.  These were as follows:

Pension Provision in other Countries

The National Pensions Review will consider alternatives to the current balance between State and private pension provisions set out in the National Pensions Policy Initiative.  It was therefore necessary to examine the range of pension models in other jurisdictions.

This project required a summary of the pension provision system, both First and Second Pillar in a number of countries.  The summary included :

- A description of the First and Second Pillar Pension Provisions

- Information on pension coverage and adequacy

- Pension issues particular to the country, including any proposed changes

- A summary of the issues relevant to Ireland which have arisen in those countries

This project was awarded to Mercer Human Resource Consulting.  It has been completed and was input to Board Workshop 2.

Benefit Options at Retirement

Among the issues being considered in the National Pensions Review is the structure of benefit options at retirement under the Second Pillar.  This includes a review of the current (Irish) arrangements for benefit provision at retirement and considers what form of benefits should be available to pension savers at retirement and the extent to which savers should have discretion.  The topics considered included:-

- Lifetime annuity

- Lump sums

- Drawdown

- Dependants’ pension

- Benefit on death after retirement

This project was awarded to Hewitt Associates Limited.  It has been completed and was input to Workshop 3.

Possible State Involvement in Second Pillar Provision

The National Pensions Review examines the advantages and disadvantages of possible State involvement in income provision at retirement under the Second Pillar.

Such an arrangement could potentially comprise some or all of the following functions:

- Providing pensions to retired members of defined benefits schemes in voluntary wind-up in exchange for lump sums

- Providing pensions to all defined benefit schemes in wind-up

- Providing pensions to all pension schemes, PRSAs and RACs, possibly up to a maximum amount

This project was awarded to Hewitt Associates Limited.  The deadline for completion is 29 July.

Pension Systems Assessment

As part of the National Pensions Review, a number of different pension provision systems will be assessed.  Part of the assessment of these systems comprises an examination of the cost and sustainability, including the fiscal and economic impact, and a comparison with the current Irish pension system.  This assessment includes a quantitative assessment and a qualitative assessment.

The range of pension systems to be considered were expected to include the following broad approaches:

- Continued voluntary Second Pillar (with/without enhanced State incentives);

- Mandatory Second Pillar provision (with/without a contribution cap); and

- Increased mandatory First Pillar pension (funded/unfunded).

See Section 8 for details of the pension systems now selected.

In addition to detailed specific quantitative projections it will include an assessment (both qualitative and as far as possible quantitative) of each of the systems being projected to include:

- Sustainability

- Direct and indirect Exchequer costs

- Economic/competitive/employment impacts

- Inter-generational equity

- Intra-generational (re)distributive effects

- Likely administration costs and efficiency in comparison with the current pension arrangements and in comparison with other systems

- The relative merits of funding versus pay as you go

- Effect on the national savings rate

Inherent in consideration of increased mandatory First Pillar pension would be an assessment of the relative merits of State support via continued tax expenditure to the Second Pillar vis-à-vis cash expenditure of equivalent amount under an enhanced First Pillar.

This project was awarded to a joint team of Life Strategies Limited and the Economic and Social Research Institute.  The deadline date for this project is 22 July.

6.	CONSULTATION

A consultation process took place between March and May 2005.  Representative bodies were contacted directly by letter and a general consultation notice was posted on the Pensions Board’s website.

22 written submissions were received to date which included submissions from:

- Irish Brokers Association

- ISME

- Irish Insurance Federation

- Irish Association of Pension Funds

- Irish Institute of Pension Managers

- Irish Association of Investment Managers

- Irish Congress of Trade Unions

- The Consumers Association of Ireland

- Cork Regional Executive of IBEC

- 13 submissions from individuals.

Meetings also took place with some organisations where input was received.

These submissions are currently being fully analysed.  Depending on time of availability some of the submission material was also fed into specific Workshop Agenda items.

7.	PENSIONS BOARD WORKSHOPS

The Pensions Board scheduled four Workshops to provide an opportunity for discussion on the substantive issues and to capture the range of views available.  Discussion was facilitated by expert presentations on relevant topics.  The Workshops were attended by Board members, other nominees of Board members, Board staff and consultants.

Agenda

Agendas for Workshops 1, 2 and 3 were as follows:

Workshop 1 on 20 April

- National Pensions Review process and project plan

- Workshop participants’ issues and expectations

- Review of NPPI targets and progress

Workshop 2 on 18 May

- Pension systems criteria

- Identifying the main types of pension system

- Identification of pension systems for assessment

Workshop 3 on 8 June

- Benefit options at retirement

- State involvement in Second Pillar provision

- Possible enhancements to voluntary provision

- Retirement age and longevity

- State support and equity

Workshop 4

Workshop 4 will be held on 2 September and the Agenda will be:

- Agreement on Final Recommendations

8.	PENSION SYSTEMS FOR ASSESSMENT

Criteria

The criteria considered appropriate for selecting pension systems were as follows:

- Coverage

- Adequacy

- Cost

- Simplicity

- Continuity

- Modernisation

- Redistribution

- Competitiveness

- Choice

- Robustness

- Acceptability

Systems Selected

The following are the systems selected for assessment for the Pensions Board by Life Strategies/ESRI:

System 1 – enhancement of current voluntary supplementary system

	Contributory old age pension of 34% of average industrial earnings (i.e. no change to current system)

	Voluntary supplementary pension system

	Tax credit on employee contributions at 42%: equivalent benefit for non-taxpayers.  Maximum qualifying income equal to current PRSA/RAC income limit.

	Employer contributions allowable as a business expense up to the PRSA/RAC limits.

	Investment income free of tax

	No change to the taxation of pension benefits.

System 2 – mandatory supplementary private system

	Contributory old age pension of 34% of average industrial earnings (i.e. no change to current system)

	Mandatory supplementary pension system, comprising 5% employer/5% employee contributory (see notes below) to a maximum of twice average industrial earnings.  Earnings below the current PRSI minimum will be exempt.

	Further voluntary employer and employee contributions permitted, and qualify for tax relief.

§	Tax credit on employee contributions at highest income tax rate: equivalent benefit for non-taxpayers.  Maximum qualifying income equal to current PRSA/RAC income limit.

	Employer contributions allowable as a business expense up to the PRSA/RAC limits.

	Investment income free of tax

	No change to the taxation of pension benefits.

System 3 – mandatory supplementary state defined contribution system

	Contributory old age pension of 34% of average industrial earnings (i.e. no change to current system)

	Mandatory supplementary state defined contribution system, comprising 5% employer/5% employee contributory (see notes below) to a maximum of twice average industrial earnings.  Earnings below the current PRSI minimum will be exempt.

	Further voluntary employer and employee contributions permitted, and qualify for tax relief.

§	Tax credit on employee contributions at highest income tax rate: equivalent benefit for non-taxpayers.  Maximum qualifying income equal to current PRSA/RAC income limit.

	Employer contributions allowable as a business expense up to the PRSA/RAC limits.

	Investment income free of tax

	No change to the taxation of pension benefits.

System 4 – mandatory supplementary state earnings related system

	Contributory old age pension of 34% of average industrial earnings (i.e. no change to current system)

	Mandatory supplementary state earnings related system to a maximum of twice average industrial earnings.  Earnings below the current PRSI minimum will be exempt.  Benefit of 1% of revalued annual earnings for each year of contribution.  The contribution rate would be calculated to be cost-neutral in the long-term, and would for projection purposes be divided equally between employees and employers.

§	Further voluntary employer and employee contributions permitted, and qualify for tax relief.

§	Tax credit on employee contributions at highest income tax rate: equivalent benefit for non-taxpayers.  Maximum qualifying income equal to current PRSA/RAC income limit.

	Employer contributions allowable as a business expense up to the PRSA/RAC limits.

	Investment income free of tax

§	No change to the taxation of pension benefits.

System 5 – enhanced basic pension, voluntary supplementary provision

§	Contributory old age pension of 50% of average industrial earnings.  The additional cost of this benefit would be met by a separately identifiable charge.

	Voluntary supplementary pension system

	Tax relief on employee contributions at marginal income tax rate.  Maximum qualifying income equal to current PRSA/RAC income limit.

	Employer contributions allowable as a business expense up to the PRSA/RAC limits.

	Investment income free of tax

§	No change to the taxation of pension benefits.

Notes on assumptions

- The level of First Pillar pension should be assumed to take immediate effect.

- The suggested pensions to be included in modelling are all pension expenditure to those over 65 (both Social Insurance and Assistance based).  This would include old age, invalidity, and widows.

- All limits and thresholds should be assumed to move in line with earnings.

- All of the systems to be examined include a voluntary supplementary component.  Clearly the take up of this will differ from the current take-up because of changes to the other components of pension provision.  The assumed rate of take-up will depend both on the details of the system being considered and on how LS/ESRI intend to model voluntary coverage.  This should be discussed further.

Associated Issues

A number of possibilities and issues will also be considered in the context of some or all of these models.  These are:

- Benefit options at retirement

- State involvement in Second Pillar provision

- Possible enhancements to voluntary provision

- Retirement age and longevity

- State support and equity

- Female coverage

- Governance (insofar as it affects coverage and adequacy)

- TIMEFRAME

Project Finalisation

The dates for finalisation of the two on-going external consultancy projects are as follows:-

- Pension Models Selected for Analysis project to be finalised by 22 July

- Possible State Involvement in Second Pillar Provision project to be finalised by 29 July

Report Approval

The scheduled dates for this are as follows:-

- Pensions Board Workshop 4 on 2 September

- Special Pensions Board Meeting on 28 September

Review Finalisation

This will involve presentation of the National Pensions Review Report to the Minister for Social and Family Affairs in early October.

10.	FINAL REPORT CONTENTS

- Executive Summary

- Introduction and background

  - Introduction

  - Process

2.3	NPPI report

2.4	Subsequent developments

3.	Review of NPPI targets

3.1     Replacement income

3.2     First Pillar target

3.3     Supplementary coverage

4.	Current coverage and adequacy

4.1	Overview

4.2      First Pillar

4.3      Supplementary coverage

4.4      Adequacy

5.	Review of current pension systems and prospects

5.1      First Pillar overview and outlook

5.2      Supplementary pension overview

5.3      Supplementary pension outlook

5.4      Other savings

5.5      Summary

6.	Obstacles to achieving NPPI targets

7.	Suggested enhancements to current systems

8.	Alternative pension systems

8.1	Overview

8.2	Alternative models

8.3	Further investigation

9.	Support for first pillar versus second pillar

10.	Criteria

11.	Sustainability of current system

12.	Assessment of alternatives and enhancements

12.1	Process

12.2	Assessment of major models

12.3.	Enhancements to current system

13.	Retirement age and longevity

13.1	Background

13.2	Impact of increasing longevity

13.3	Possible responses

14.	Benefits at retirement

15.	State annuity fund, etc.

16.	Considerations and recommendations

17.	Related issues

Will include governance, PRSA regulation

Appendices